## Sheet1
Sprint 1
Type | Task name | Est time | Status | Assigned to | Total Hours spent
Research | Select site building tools (Language/ software/ imports) | 3 | To do | ES | JC: 3 + (2)
Research | Create/ refine site wireframe based on existing design | 3 | To do | JC | RF: (6)
Research | find Recipe APIs and assess compatability | 2 | To do | KJ, RF | KJ: (6) | :)
Research | Find Barcode scanners and assess compatability | 2 | To do | KJ, RF | GM: 3 + (3)
Research | Test compatability between scanned items and finding recipes | 2 | To do | KJ, RF | ES: 3 + (3)
Research | Similar product investigation (Features/ layouts) | 2 | To do | JC, MB | MB: 3 + (2)
Research | Design database layouts (User storage/ User inventory) | 3 | To do | GM
Research | Find database tools with web app compatability | 3 | To do | GM, ES
Research | Research log in systems within web apps | 3 | To do | MB
23